## Sheet1
Task | Lab Name | Done in Lab | Calder Due Date | Completed? | Who?
Organization Overview | N/A |  |  | YES | Irvin
The Design Problem | Strategic Design | Tu, Oct 5 | Mon, Nov 1 | YES | Calder
User Analysis | Persona | Tu, Oct 12 | Fri, Nov 5 | YES | Calder
High Level System Req | Requirements | Tu, Oct 19 | Wed, Nov 10 | YES | C
Information Analysis | IA | Tu, Oct 26 | Sat, Nov 13 | YES | B
| Content Modeling | Tu, Nov 2 | Tue, Nov 16 | YES | A
Activity and Interaction Analysis | Activity | Tu, Nov 9 | Fri, Nov 19 | YES | C
| Interactions | Tu, Nov 16 | Mon, Nov 22 | YES | B
Prototype | Prototype | Tu, Nov 23 | Mon, Nov 29 | YES | A
Design Evaluation | Usability | Tu, Nov 30 | Fri, Dec 3 | YES | B
| TOTAL PARTS LEFT TO COMPLETE | 0
| Project Due: | Tu, Dec 7
Team Name
|  |  | A | Dan / Aaron
|  |  | B | Pei-Wen / Irvin
|  |  | C | Kathryn / Ryan